## Journal
|  |  |  | 1900-01-04 14:10 | Re-Book
Datum | Start Zeit | Ende Zeit | Pause Zeit | Netto Zeit | Vorname Nachname jede/r rapportiert für sich selbst | Code aus dem PSP | Tätigkeit eigene Leistung, erzielte Fortschritte, Schwierigkeiten und Erfolge | Commit URL https://github.com/.../commit/xyz
2025-02-04 | 13:55 | 17:30 | 0:45 | 2:50 | Dario Joel Lopez | BDS - 01 | Auf Visio Relationales Modell mit Alex besprochen
2025-02-04 | 13:55 | 15:50 | 0:10 | 1:45 | Alex Belik |  | Tables and database relations
2025-02-04 | 13:55 | 17:10 | 0:20 | 2:55 | Laura Gjoni | FD - 01 | I created the framework for the home page and also completed it | https://github.com/ipt-9/Re-Book/commit/9d109509467e363c6850bcf02e500ad74a7e81bf
2025-02-04 | 16:10 | 17:15 |  | 1:05 | Alex Belik |  | Create database, tables, columns
2025-02-11 | 13:30 | 17:10 | 0:20 | 3:20 | Alex Belik | BDC - 01 | Configure connection | https://github.com/ipt-9/Re-Book/commit/9ab22c2b2584e80ce714aa96c72305df992637b7
2025-02-11 | 13:30 | 14:00 | 0:10 | 0:20 | Dario Joel Lopez | BDS - 01 | Corrected Mistakes and added relationships in the relational model
2025-02-11 | 14:00 | 14:45 | 0:00 | 0:45 | Dario Joel Lopez | BDS - 02.02 | Added the foreign key constraints with SQL
2025-02-11 | 15:10 | 15:30 | 0:00 | 0:20 | Dario Joel Lopez | BDD - 01 | Added the dummy data
2025-02-11 | 12:30 | 15:45 | 0:25 | 2:50 | Laura Gjoni | FD - 01 | Completed the Search and Browse Page | https://github.com/ipt-9/Re-Book/commit/e5ee48aa9e5f35f50595f5b81fa66586c26dd21a
2025-02-11 | 15:45 | 17:30 | 0:10 | 1:35 | Laura Gjoni | FD - 01 | Completed the Sell Page and added the pictures | https://github.com/ipt-9/Re-Book/commit/7c65557139e03a29bdca8c6c904daaa02f9a8504
2025-02-11 | 15:30 | 17:10 | 0:15 | 1:25 | Dario Joel Lopez | BDC - 01 | Worked on the connection, didn't work
2025-02-18 | 13:05 | 14:40 | 0:10 | 1:25 | Dario Joel Lopez |  | Attendet the Demo
2025-02-18 | 13:05 | 14:40 | 0:10 | 1:25 | Alex Belik |  | Attendet the Demo
2025-02-18 | 15:15 | 17:15 | 0:10 | 1:50 | Dario Joel Lopez | BFU - 01 | Did the CRUD-Operations on php, but have to find out how to add functioning php files to angular projects
2025-02-18 | 15:15 | 17:15 | 0:15 | 1:45 | Alex Belik | BDC - 02 | established the database connection and tested it according to the changes
2025-02-18 | 12:35 | 15:00 | 0:00 | 2:25 | Laura Gjoni | FD - 01 | Design of Privacy Policy & Terms of Service Pages | https://github.com/ipt-9/Re-Book/commit/cb344e71108aab104f616f1d68c73919a4d263fc
2025-02-18 | 15:15 | 16:30 | 0:15 | 1:00 | Laura Gjoni | FD - 01 | Design Contact, About Us, Checkout, Cart, Favorites Pages | https://github.com/ipt-9/Re-Book/commit/8c95a8c916f5fd1c7804eef35ac9c18214c6a08e
2025-02-18 | 16:30 | 17:15 | 0:00 | 0:45 | Laura Gjoni | FD - 01 | Working on Login, Register and Profile | https://github.com/ipt-9/Re-Book/commit/5c53b75a2b3c159cc2765a2f05cb1fd6e2a02870
2025-02-18 | 17:00 | 17:30 | 0:00 | 0:30 | Laura Gjoni | DP - 01 | Done the Status report
2025-03-11 | 13:00 | 17:20 | 0:25 | 3:55 | Laura Gjoni | FD - 01 | Finished the design without logic | https://github.com/ipt-9/Re-Book/commit/8df72d28084df3ed2f0d3c46051920041759f9e5
2025-03-11 | 13:00 | 17:30 | 0:30 | 4:00 | Alex Belik |  | Code Review from Sprint 1
2025-03-11 | 13:00 | 17:30 | 0:35 | 3:55 | Dario Joel Lopez |  | Code Review from Sprint 1
2025-03-18 | 13:00 | 14:30 | 0:05 | 1:25 | Alex Belik |  | Redownload the environment
2025-03-18 | 14:55 | 17:30 | 0:10 | 2:25 | Alex Belik |  | Website upload on plesk, slight adjustments in code
2025-03-25 | 13:00 | 17:30 | 0:25 | 4:05 | Alex Belik |  | Function "Book Upload" + data gets saved in the database
2025-03-25 | 12:30 | 17:20 | 0:25 | 4:25 | Laura Gjoni | FD - 04 | Translated, improved, navbar and footer outsourced | https://github.com/ipt-9/Re-Book/commit/fcf7c04bdf4249d8bf8974687b417b29d3a38ee1
2025-03-25 | 12:30 | 17:20 | 0:30 | 4:20 | Dario Joel Lopez |  | Tried to fix an error revolving login and register
2025-04-01 | 9:00 | 11:20 | 0:10 | 2:10 | Alex Belik |  | I uploaded all the files to the server and made it work.
2025-04-01 | 12:30 | 17:00 | 0:10 | 4:20 | Alex Belik | FD - 01 | I fixed the login and register that stopped working. I uploaded the files to the server. | https://github.com/ipt-9/Re-Book/commit/577c5adb3180d2a38f216b3b9b2fa8b675df4221
2025-04-01 | 12:30 | 17:20 | 0:15 | 4:35 | Laura Gjoni | DP - 02 | Done the second Status Report
2025-04-01 | 12:30 | 17:20 | 0:30 | 4:20 | Dario Joel Lopez |  | Started working on the upload listing functionality
2025-04-08 | 12:30 | 14:30 | 0:05 | 1:55 | Dario Joel Lopez |  | Worked on the github work packages for sprint 3 |  | d | d | d
2025-04-08 | 15:15 | 15:50 | 0:00 | 0:35 | Dario Joel Lopez |  | Potentially finished the upload listing functionality
2025-04-08 | 12:30 | 14:00 | 0:00 | 1:30 | Laura Gjoni
2025-04-08 | 14:00 | 17:15 | 0:25 | 2:50 | Laura Gjoni |  | Created Filter function and navigation from homepage to browse | https://github.com/ipt-9/Re-Book/commit/7383d482189df3512c63122c2d0482a9f86d9c0b
2025-04-08 | 16:00 | 17:15 | 0:20 | 0:55 | Dario Joel Lopez |  | Changed the database after consulting with Alex
2025-04-08 | 13:00 | 14:20 | 0:10 | 1:10 | Alex Belik |  | Worked on the Arbeitspakete 3, mainly the descriptions
2025-04-08 | 14:40 | 17:15 | 0:10 | 2:25 | Alex Belik |  | Switched the hard coded data with the database data
2025-04-14 | 9:00 | 11:00 | 0:00 | 2:00 | Alex Belik |  | Worked on new Git problems
2025-04-14 | 9:00 | 11:00 | 0:00 | 2:00 | Dario Joel Lopez |  | Worked on git merging problems
2025-04-14 | 9:00 | 11:00 | 0:00 | 2:00 | Laura Gjoni |  | Worked on the token problem
2025-04-14 | 12:00 | 16:20 | 0:00 | 4:20 | Alex Belik |  | Worked on the Browsing page.
2025-04-14 | 12:00 | 16:20 | 1:00 | 3:20 | Dario Joel Lopez |  | Tried to connect the upload-listing logic with the user validation
2025-04-14 | 12:00 | 16:20 | 0:00 | 4:20 | Laura Gjoni |  | Fixed the problem with the user token
2025-04-15 | 12:30 | 17:20 | 0:25 | 4:25 | Laura Gjoni | BFU - 04 | The user information from the login/register is now displayed on the profile dashboard | https://github.com/ipt-9/Re-Book/commit/038545d7007687cfed0c3d79cfe30f0747986453
2025-04-15 | 12:25 | 15:50 | 0:25 | 3:00 | Dario Joel Lopez |  | Tried to complete the upload-listing logic with user validation
2025-04-15 | 15:50 | 16:00 | 0:00 | 0:10 | Dario Joel Lopez |  | Filled the database image with the required paths and tested if it would show on the frontend with Alex
2025-04-15 | 16:00 | 17:20 | 0:15 | 1:05 | Dario Joel Lopez |  | Worked on fixing an issue regarding authorization with user tokens, still doesn't work though
2025-04-15 | 12:20 | 17:10 | 0:30 | 4:20 | Alex Belik |  | Finished the browsing page, connected to the database and all worked. Also doen the product page with the correct product.
2025-04-16 | 9:00 | 12:00 | 0:25 | 2:35 | Dario Joel Lopez |  | Fixed the problem with the user token authorization and worked on connecting the logic with the frontend
2025-04-16 | 13:00 | 15:50 | 0:30 | 2:20 | Dario Joel Lopez |  | Tried connecting the upload-listing backend with the frontend
2025-05-06 | 12:30 | 15:30 | 0:25 | 2:35 | Laura Gjoni | DP - 02 | Done the third Status Report
2025-05-06 | 15:30 | 17:20 | 0:00 | 1:50 | Laura Gjoni |  | Helped the others with issues
2025-05-06 | 12:25 | 17:00 | 0:45 | 3:50 | Dario Joel Lopez |  | Working on making the logout work in the frontend, so fixed an error where it doesn't work on the frontend but works in the backend
2025-05-06 | 17:00 | 17:30 | 0:00 | 0:30 | Dario Joel Lopez |  | Worked on the upload-listing, but it didn't work due to missing fields or some issues with the image, not sure yet
2025-05-10 | 18:40 | 21:40 | 0:20 | 2:40 | Dario Joel Lopez |  | Worked on getting the upload-listing to work with Alex
2025-05-11 | 17:00 | 18:40 | 0:20 | 1:20 | Dario Joel Lopez |  | Made new realistic inputs to feed into the database
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00

## Team
Vorname Nachname jede/r rapportiert für sich selbst
Dario Joel Lopez
Laura Gjoni
Alex Belik

## PSP
Code aus dem PSP | Bezeichnung aus dem PSP
DP - 01 | We are writing a first report about our project. We will record all progress there until then
BDS - 01 | Create a Relational Model for our database
BDS - 02 | Create the database
BDS - 02.01 | Define Tables
BDS - 02.02 | Define Columns
BDD - 01 | Dummy Data
BFU - 01 | Backend logic for registering a new User (insert into database)
BDC - 01 | Configure the connection
BDC - 02 | Establish the connection
BDC - 03 | Test connection
BFU - 02 | Backend logic for a login function for an existign user (select and check from database)
BFU 02.01 | Backend logic to check if the password from the input is the same as the one in the database
BFU - 03 | Backend logic to logout
FD - 01 | Write code for a simple design without any functionality
FD - 02 | Adapt the coloring from figma
FD - 03 | Adapt the font from figma
BFF - 03 | Upload listing
BDD - 02 | Insert Real Data
BDR - 03 | Delete Listing
BFU - 04 | Profile Dashboard
BFU - 05 | Show user information
BFU - 06 | Edit user information
BFU - 07 | Delete user information
BFF - 01 | Filter function
BFF - 02 | Search function
BFF - 04 | Mark favourite
BFF - 05 | Shopping cart
BFF - 05.1 | Add to shopping cart
BFF - 05.2 | Edit shopping cart
BFF - 05.3 | Delete shopping cart
FD - 04 | Add design that needs logic
DP - 02 | Report 01.04.2025