## Journal
|  |  |  | 1900-01-05 12:44 | Re-Book
Datum | Start Zeit | Ende Zeit | Pause Zeit | Netto Zeit | Vorname Nachname jede/r rapportiert für sich selbst | Code aus dem PSP | Tätigkeit eigene Leistung, erzielte Fortschritte, Schwierigkeiten und Erfolge | Commit URL https://github.com/.../commit/xyz
2025-02-04 | 13:55 | 17:30 | 0:45 | 2:50 | Dario Joel Lopez | BDS - 01 | Auf Visio Relationales Modell mit Alex besprochen
2025-02-04 | 13:55 | 15:50 | 0:10 | 1:45 | Alex Belik |  | I defined and created the necessary tables and relationships in the database to support core application features. This included setting up foreign key constraints between users, products, orders, cart items, and favorites. The relational structure was designed to ensure data integrity, allow efficient querying, and reflect real-world logic — for example, connecting users to their listings, orders, and cart contents.
2025-02-04 | 13:55 | 17:10 | 0:20 | 2:55 | Laura Gjoni | FD - 01 | I created the framework for the home page and also completed it | https://github.com/ipt-9/Re-Book/commit/9d109509467e363c6850bcf02e500ad74a7e81bf
2025-02-04 | 16:10 | 17:15 |  | 1:05 | Alex Belik |  | I created the project’s database structure, including the necessary tables and columns for features such as user accounts, product listings, orders, and favorites. The table design was based on the functional needs of the platform and aimed at avoiding data redundancy while ensuring scalability.
2025-02-11 | 13:30 | 17:10 | 0:20 | 3:20 | Alex Belik | BDC - 01 | I configured the connection between the backend and the database, ensuring that all queries could be executed securely and reliably. This included setting up access credentials, selecting the correct port, and testing connectivity to confirm that data could be stored and retrieved as expected. | https://github.com/ipt-9/Re-Book/commit/9ab22c2b2584e80ce714aa96c72305df992637b7
2025-02-11 | 13:30 | 14:00 | 0:10 | 0:20 | Dario Joel Lopez | BDS - 01 | Corrected Mistakes and added relationships in the relational model
2025-02-11 | 14:00 | 14:45 | 0:00 | 0:45 | Dario Joel Lopez | BDS - 02.02 | Added the foreign key constraints with SQL
2025-02-11 | 15:10 | 15:30 | 0:00 | 0:20 | Dario Joel Lopez | BDD - 01 | Added the dummy data
2025-02-11 | 12:30 | 15:45 | 0:25 | 2:50 | Laura Gjoni | FD - 01 | Completed the Search and Browse Page | https://github.com/ipt-9/Re-Book/commit/e5ee48aa9e5f35f50595f5b81fa66586c26dd21a
2025-02-11 | 15:45 | 17:30 | 0:10 | 1:35 | Laura Gjoni | FD - 01 | Completed the Sell Page and added the pictures | https://github.com/ipt-9/Re-Book/commit/7c65557139e03a29bdca8c6c904daaa02f9a8504
2025-02-11 | 15:30 | 17:10 | 0:15 | 1:25 | Dario Joel Lopez | BDC - 01 | Worked on the connection, didn't work
2025-02-18 | 13:05 | 14:40 | 0:10 | 1:25 | Dario Joel Lopez |  | Attendet the Demo
2025-02-18 | 13:05 | 14:40 | 0:10 | 1:25 | Alex Belik |  | I attended a demo session led by a teacher, where we were shown how to properly work with the server environment. The session covered key aspects such as file deployment, database access, configuration settings, and using Plesk for managing the project online.
2025-02-18 | 15:15 | 17:15 | 0:10 | 1:50 | Dario Joel Lopez | BFU - 01 | Did the CRUD-Operations on php, but have to find out how to add functioning php files to angular projects
2025-02-18 | 15:15 | 17:15 | 0:15 | 1:45 | Alex Belik | BDC - 02 | I established the connection between the application and the database, adjusting the configuration to match the updated structure. After setup, I thoroughly tested the connection to ensure that data could be read and written correctly according to the recent database changes. This included validating user data access, listings retrieval, and form submissions.
2025-02-18 | 12:35 | 15:00 | 0:00 | 2:25 | Laura Gjoni | FD - 01 | Design of Privacy Policy & Terms of Service Pages | https://github.com/ipt-9/Re-Book/commit/cb344e71108aab104f616f1d68c73919a4d263fc
2025-02-18 | 15:15 | 16:30 | 0:15 | 1:00 | Laura Gjoni | FD - 01 | Design Contact, About Us, Checkout, Cart, Favorites Pages | https://github.com/ipt-9/Re-Book/commit/8c95a8c916f5fd1c7804eef35ac9c18214c6a08e
2025-02-18 | 16:30 | 17:15 | 0:00 | 0:45 | Laura Gjoni | FD - 01 | Working on Login, Register and Profile | https://github.com/ipt-9/Re-Book/commit/5c53b75a2b3c159cc2765a2f05cb1fd6e2a02870
2025-02-18 | 17:00 | 17:30 | 0:00 | 0:30 | Laura Gjoni | DP - 01 | Done the Status report
2025-03-11 | 13:00 | 17:20 | 0:25 | 3:55 | Laura Gjoni | FD - 01 | Finished the design without logic | https://github.com/ipt-9/Re-Book/commit/8df72d28084df3ed2f0d3c46051920041759f9e5
2025-03-11 | 13:00 | 17:30 | 0:30 | 4:00 | Alex Belik |  | I participated in the code review for Sprint 1, where we went through the core components of the project developed so far. This included reviewing structure, readability, and functionality of the code, identifying redundant or duplicated logic, and suggesting improvements for consistency and maintainability. I also provided feedback on naming conventions, file organization, and best practices for future development.
2025-03-11 | 13:00 | 17:30 | 0:35 | 3:55 | Dario Joel Lopez |  | Code Review from Sprint 1
2025-03-18 | 13:00 | 14:30 | 0:05 | 1:25 | Alex Belik |  | I re-downloaded and set up the development environment to ensure all tools, dependencies, and configurations were aligned with the current state of the project. This was necessary to fix local compatibility issues and to continue working smoothly.
2025-03-18 | 14:55 | 17:30 | 0:10 | 2:25 | Alex Belik |  | I uploaded the website to the Plesk server and made several small code adjustments to ensure compatibility with the server environment. This included tweaking file paths, adjusting PHP configurations, and validating that the application functions correctly online.
2025-03-25 | 13:00 | 17:30 | 0:25 | 4:05 | Alex Belik |  | I implemented the "Book Upload" feature, allowing users to submit new book listings. The uploaded data — including title, author, image, and price — is successfully saved into the database. This marks a key step in enabling user-generated content on the platform.
2025-03-25 | 12:30 | 17:20 | 0:25 | 4:25 | Laura Gjoni | FD - 04 | Translated, improved, navbar and footer outsourced | https://github.com/ipt-9/Re-Book/commit/fcf7c04bdf4249d8bf8974687b417b29d3a38ee1
2025-03-25 | 12:30 | 17:20 | 0:30 | 4:20 | Dario Joel Lopez |  | Tried to fix an error revolving login and register
2025-04-01 | 9:00 | 11:20 | 0:10 | 2:10 | Alex Belik |  | I uploaded all project files to the live server and configured everything to ensure the application runs as expected in the production environment. This included verifying database connections, file paths, and server-specific settings.
2025-04-01 | 12:30 | 17:00 | 0:10 | 4:20 | Alex Belik | FD - 01 | I fixed issues with the login and registration functionality, which had stopped working after recent changes. I reviewed the backend logic, checked the form handling, and ensured proper communication between frontend and backend. After debugging and testing, both features now work reliably again. | https://github.com/ipt-9/Re-Book/commit/577c5adb3180d2a38f216b3b9b2fa8b675df4221
2025-04-01 | 12:30 | 17:20 | 0:15 | 4:35 | Laura Gjoni | DP - 02 | Done the second Status Report
2025-04-01 | 12:30 | 17:20 | 0:30 | 4:20 | Dario Joel Lopez |  | Started working on the upload listing functionality
2025-04-08 | 12:30 | 14:30 | 0:05 | 1:55 | Dario Joel Lopez |  | Worked on the github work packages for sprint 3 |  | d | d | d
2025-04-08 | 15:15 | 15:50 | 0:00 | 0:35 | Dario Joel Lopez |  | Potentially finished the upload listing functionality
2025-04-08 | 12:30 | 14:00 | 0:00 | 1:30 | Laura Gjoni
2025-04-08 | 14:00 | 17:15 | 0:25 | 2:50 | Laura Gjoni |  | Created Filter function and navigation from homepage to browse | https://github.com/ipt-9/Re-Book/commit/7383d482189df3512c63122c2d0482a9f86d9c0b
2025-04-08 | 16:00 | 17:15 | 0:20 | 0:55 | Dario Joel Lopez |  | Changed the database after consulting with Alex
2025-04-08 | 13:00 | 14:20 | 0:10 | 1:10 | Alex Belik |  | I worked on Arbeitspaket 3, focusing primarily on refining and completing the product descriptions. I made sure the text is clear, informative, and matches the structure and tone of the platform. This was important to ensure consistency and professionalism in how products are presented.
2025-04-08 | 14:40 | 17:15 | 0:10 | 2:25 | Alex Belik |  | I replaced previously hardcoded book data with dynamic content from the database, ensuring that all product information is now loaded directly from the backend. This improved maintainability and made the application more scalable and ready for real data.
2025-04-14 | 9:00 | 11:00 | 0:00 | 2:00 | Alex Belik |  | I encountered and worked through several Git-related problems, such as merge conflicts and sync issues between local and remote branches. I resolved them by carefully reviewing commits, merging branches manually where needed, and ensuring the repository was up to date and consistent for the team.
2025-04-14 | 9:00 | 11:00 | 0:00 | 2:00 | Dario Joel Lopez |  | Worked on git merging problems
2025-04-14 | 9:00 | 11:00 | 0:00 | 2:00 | Laura Gjoni |  | Worked on the token problem
2025-04-14 | 12:00 | 16:20 | 0:00 | 4:20 | Alex Belik |  | I worked on the Browsing page, focusing on the overall layout, visual design, and functionality to fetch and display books from the database using PHP. While the basic structure is in place, the page is not yet complete due to errors in data retrieval and display logic, which still need to be resolved.
2025-04-14 | 12:00 | 16:20 | 1:00 | 3:20 | Dario Joel Lopez |  | Tried to connect the upload-listing logic with the user validation
2025-04-14 | 12:00 | 16:20 | 0:00 | 4:20 | Laura Gjoni |  | Fixed the problem with the user token
2025-04-15 | 12:30 | 17:20 | 0:25 | 4:25 | Laura Gjoni | BFU - 04 | The user information from the login/register is now displayed on the profile dashboard | https://github.com/ipt-9/Re-Book/commit/038545d7007687cfed0c3d79cfe30f0747986453
2025-04-15 | 12:25 | 15:50 | 0:25 | 3:00 | Dario Joel Lopez |  | Tried to complete the upload-listing logic with user validation
2025-04-15 | 15:50 | 16:00 | 0:00 | 0:10 | Dario Joel Lopez |  | Filled the database image with the required paths and tested if it would show on the frontend with Alex
2025-04-15 | 16:00 | 17:20 | 0:15 | 1:05 | Dario Joel Lopez |  | Worked on fixing an issue regarding authorization with user tokens, still doesn't work though
2025-04-15 | 12:20 | 17:10 | 0:30 | 4:20 | Alex Belik |  | I completed the browsing page, successfully connected it to the database, and ensured that all product listings were dynamically loaded and displayed correctly. In addition, I developed the product detail page, which retrieves and displays the correct product information based on the selected item. Both pages now work seamlessly together and provide a smooth user experience from browsing to viewing individual listings.
2025-04-16 | 9:00 | 12:00 | 0:25 | 2:35 | Dario Joel Lopez |  | Fixed the problem with the user token authorization and worked on connecting the logic with the frontend
2025-04-16 | 13:00 | 15:50 | 0:30 | 2:20 | Dario Joel Lopez |  | Tried connecting the upload-listing backend with the frontend
2025-05-06 | 12:30 | 15:30 | 0:25 | 2:35 | Laura Gjoni | DP - 02 | Done the third Status Report
2025-05-06 | 15:30 | 17:20 | 0:00 | 1:50 | Laura Gjoni |  | Helped the others with issues
2025-05-06 | 12:25 | 17:00 | 0:45 | 3:50 | Dario Joel Lopez |  | Working on making the logout work in the frontend, so fixed an error where it doesn't work on the frontend but works in the backend
2025-05-06 | 12:25 | 17:00 | 0:40 | 3:55 | Alex Belik |  | I focused on implementing the core functionality of the shopping cart, specifically enabling users to add products to their cart. A major challenge throughout the day was handling invalid JSON responses between the frontend and backend.
2025-05-06 | 17:00 | 17:30 | 0:00 | 0:30 | Dario Joel Lopez |  | Worked on the upload-listing, but it didn't work due to missing fields or some issues with the image, not sure yet
2025-05-10 | 18:40 | 21:40 | 0:20 | 2:40 | Dario Joel Lopez |  | Worked on getting the upload-listing to work with Alex
2025-05-11 | 17:00 | 18:40 | 0:20 | 1:20 | Dario Joel Lopez |  | Made new realistic inputs to feed into the database
0:00
2025-05-10 | 9:00 | 23:59 | 1:00 | 13:59 | Alex Belik |  | This was one of the most productive and intensive days of development. I worked across multiple features, starting with a full rebuild of the shopping cart display and logic. Items in the cart are now properly separated and formatted, with clear visual structure and individual remove functionality. I also completed the entire checkout process. This included designing the checkout page, implementing purchase processing, and connecting it to the database. Once a payment is processed, the system now records the order in the database and marks the purchased listings accordingly (e.g., marked as sold). This update made the whole cart-to-checkout flow fully functional and ready for real user interaction. To support this, I made several improvements to the database structure, optimizing it to avoid redundant data and make it more scalable for real-world use. I revised several PHP files to fix logic issues, validate incoming requests more thoroughly, and improve overall error handling. I also ensured the delete functionality in the cart works as expected — allowing users to remove individual items cleanly. Also, the displaying of books on the profile was improved to match the checkout logic and show the correct books. The upload listing was also an issue we were working on for quite a while. After some effort with the help from Dario, we made it work, and I also implemented the correct way to upload the images to the server so they get displayed accordingly. Here we again got the JSON error but solved it pretty fast. Beyond these backend and logic updates, I also made improvements to several other key parts of the platform: On the Favorites page, I worked on layout and data retrieval so that saved items are correctly displayed to users. The user can also now click the heart emoji next to the product, and it gets added to the favorite table in the database. In the Profile section, I cleaned up the interface and spacing between the sections. I worked closely with Dario to align frontend behavior with backend logic and to test the entire flow from browsing to checking out thoroughly. | d708bea3677e832f8878c832b1336b1ef83151c4 , 2705f15da3b39ba205ddaa08a6111a6f7508a3d3 , 30292aaa3f76163087904f4c3c24b1c4fded7f1f , 65c1acb14866780fb6c2954d80dc2226051fe108, 2a0f8b41c68c3b13611bec017b46a5ebf62f8d53 , f66a4201a7bf23454fc05884ddcab0049775e5a2 , b0fe03eb3cb25fa94eb461c1d6d999b0dfd72fc7 , f8ee32c3704a6c4feb5906b4953cfc71a1f22ad8 , 0ea2a4bd6a1b1ca31ed0a509f074cced65a43370
2025-05-11 | 16:00 | 21:00 | 0:20 | 4:40 | Alex Belik |  | This day was mainly focused on polishing the UI and finalizing the project for the showcase. I refined the CSS of the cart page, making sure that each element was visually aligned — especially ensuring that prices and action buttons appear consistently on the right. I also handled a few last-minute layout changes that were needed to improve readability. The entire cart and checkout system was tested again to ensure stability. I reviewed database entries, validated payment records, and confirmed that products were properly marked after purchase. | https://github.com/ipt-9/Re-Book/commit/c481cbeb0b8ce7a7497248777a319c49c27d2e44
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00

## Team
Vorname Nachname jede/r rapportiert für sich selbst
Dario Joel Lopez
Laura Gjoni
Alex Belik

## PSP
Code aus dem PSP | Bezeichnung aus dem PSP
DP - 01 | We are writing a first report about our project. We will record all progress there until then
BDS - 01 | Create a Relational Model for our database
BDS - 02 | Create the database
BDS - 02.01 | Define Tables
BDS - 02.02 | Define Columns
BDD - 01 | Dummy Data
BFU - 01 | Backend logic for registering a new User (insert into database)
BDC - 01 | Configure the connection
BDC - 02 | Establish the connection
BDC - 03 | Test connection
BFU - 02 | Backend logic for a login function for an existign user (select and check from database)
BFU 02.01 | Backend logic to check if the password from the input is the same as the one in the database
BFU - 03 | Backend logic to logout
FD - 01 | Write code for a simple design without any functionality
FD - 02 | Adapt the coloring from figma
FD - 03 | Adapt the font from figma
BFF - 03 | Upload listing
BDD - 02 | Insert Real Data
BDR - 03 | Delete Listing
BFU - 04 | Profile Dashboard
BFU - 05 | Show user information
BFU - 06 | Edit user information
BFU - 07 | Delete user information
BFF - 01 | Filter function
BFF - 02 | Search function
BFF - 04 | Mark favourite
BFF - 05 | Shopping cart
BFF - 05.1 | Add to shopping cart
BFF - 05.2 | Edit shopping cart
BFF - 05.3 | Delete shopping cart
FD - 04 | Add design that needs logic
DP - 02 | Report 01.04.2025